## Sheet1
Bug ID | Title/Summary | Description |  |  |  | Severity | Priority | Environment | Status
|  | Precondition | Test steps | Expected result | Actual result
BID_01 | Register without following credential rule | user is on homepage | 1. Fill all fields with valid info but not follow credential rule for username and password. | show message that enter valid username and password | Account created successfully | medium | high | OS : window 10 browser: chorme | new
2.click register button.
BID_02 | Register with invalid information | user is on homepage | 1. Fill all fields within invalid info of phone ,city,state and zipcode. | error message to enter the valid information | Account created successfully | high | high | OS : window 10 browser: chorme | new
2.click register button.
BID_03 | Register with existing username | user is on homepage | 1. Fill all fields with valid info with existing username | error message that user is already exist | Account created successfully | critical | high | OS : window 10 browser: chorme | new
2. Click regster button.
BID_04 | Login with invalid credentials | user is on homepage | 1. enter invalid username and password | show message user is not exist | User logged in successfully | medium | high | OS : window 10 browser: chorme | new
2. Click Log in button.
BID_05 | Transfer with blank amount data | user is logged in and have atlest one account. | 1.go to trasfer funds option | show message to enter appropriate amount to transfer. | Funds transfered successfully | medium | high | OS : window 10 browser: chorme | new
2. don’t enter any amount
3. select accounts to transer funds
4. click on transfer button.
BID_06 | Transfer to same account | user is logged in and have atlest one account. | 1.go to trasfer funds option | not allow transfer and show warning message that accounts are same. | Funds transfered successfully | medium | medium | OS : window 10 browser: chorme | new
2. enter amount to transfer
3. select same account to transfer
4. click on transfer button.
BID_07 | Pay a bill with 0 amount | user is logged in and have atlest one account. | 1. fill the form and add 0 in amount field | show message that entervalid amount | bill payment completed | high | high | OS : window 10 browser: chorme | new
2. click on sent payment
BID_08 | Pay a bill with more amount than balance of account | user is logged in and have atlest one account. | 1. fill the form and add 0 in amount field | show message that insufficient balance | bill payment completed | critical | high | OS : window 10 browser: chorme | new
2. click on sent payment
BID_09 | Loan amount equal to Down payment | user is logged in | 1. go to request loan option | Should allow and show correct approval or rejection | Loan approved | medium | high | OS : window 10 browser: chorme | new
2. enter same amount in both fields
3. Click on apply
BID_10 | Enter invalid email and phone number(format) | user is logged in | 1. go to customer care | show message to enter valid info | show message to enter info | low | low | OS : window 10 browser: chorme | new
2. enter invalid email and phone
3. Click on apply